## Sheet1
Risk | Effect | Cause | Probability | Severity | Mitigating Actions | Date Recognised | Date Mitigated and Action Taken | Review
Project Level Threats
Project Not Finished on Time | Failure to complete the project on time will lead to a lower quality product. A lower quality product will inevitably lead to a lower overall mark. | Not completing tasks in the expected timeframe. Over-engineering of the solution. Shifting Deadlines | 3 | 4 | Ensure that all planned features/tasks can be completed in a reasonable, project specific timeframe. Allow for shifting deadlines by providing the MVP before adding other features. Attempt to create a buffer, aiming to have the project completed in advance of the deadline. | 2023-01-16 | Not mitigated. | This risk unfortunately did impact our team, as we were unable to get beyond a certain part of our pipeline process we were, until the last minute working on finding a solution.
Cloud Infrastructure Not Available | Inability to use our provisioned resources could preclude us from being able to develop/present our solution. | Data center outages. | 1 | 3 | As we do not have any control over the AWS services from an uptime perspective, we are not able to mitigate this risk. Due to the very high reliability of the AWS infrastructure however, this risk is extremely unlikely to arise. Furthermore, if this risk did occur, it is likely that AWS would fix the problem before it impacted us in any noticeable way. | 2023-01-16 | Not mitigated. | As expected, this risk did not arise during the project.
Poor Communication Between Team Members. | Inability to collaborate effectively could cause the final solution to be disjointed. | Not utilising the appropriate channels of communication. Poor organisation of resources. Personal clashes. | 2 | 4 | By setting up proper means of communicating our ideas and resources with one another, we can mitigate this risk. Additionally, using our soft skills to carefully communicate with one another reduces the chances of personal clashes. | 2023-01-16 | 16/01/2023: Implementing a central GitHub repository allowed for easy file sharing and version control. Setting up a Trello board alllowed us to easily keep track of our tasks. Through the use of MS Teams, Discord and Slack, we were able to stay in near constant communication. | Due to the mitigating actions that we took, we were able to avoid this risk.
Team Member/s Unavailable | A team member dropping out from the project for any reason could be detrimental to the project, depending on their responsibilities and whether another person can take their place. | Illness. Injury. Bereavement. | 2 | 4 | Due to the unpredictable nature of this risk, no meaningful mitigating actions can be taken. | 2023-01-16 | Not mitigated. | Thankfully, this risk didn't apply to any of our group members.
Solution Threats
Inability to Apply Intended Solution to Application | Inability to implement our solution to this problem would essentially mean that we have failed in our task. We would not be able to provide the client with a working solution. | Inexperience with porting an application to work across several machines. Mistaken assumptions about what would constitute a working solution. Difficulties with using the tools that comprise our solution. | 3 | 4 | Ensure that the planned solution is understood and agreed upon by all team members. Spend some time learning about the tools that we need to use. Implement tools with which we are already familiar. | 2023-01-18 | 18/01/2023: Upon realising that we were not clear on the exact route to take with our solution, we aimed to course correct and stick to a unified plan. | Realising that we were not in sync regarding the exact implementation of our solution at this late stage of our project meant that we had to scramble to get our solution to work until the last minute.
Webhooks Don't Initiate Build on New Deploy | New pushes to the application's repository should trigger a new build on the pipeline. If this is non-functional, a developer's work may not be implemented. | Improper configuration of the webhooks responsible for detecting changes to the code repository. | 2 | 2 | Test the webhooks extensively to ensure that they are correctly triggering the build pipeline. | 2023-01-17 | Not mitigated. | At the moment of writing, the webhooks have not yet been configured and as such cannot be tested.
Limited Cloud Permissions | Limited permissions could necessitate the use of tools which we have not planned to use. | Limited permissions granted from an administration level. | 3 | 3 | Try to work around restrictions. Request access from administrator. | 2023-01-18 | 19/01/2023: In order to bypass the restrictions, we created a personal AWS account. Had we taken this action earlier in the project we might have been able to achieve more. | Delay in creating our own personal account cost us a lot of time.
Changes to Project Requirements | Changing requirements could necessitate a change to the planned solution. As this change could be major or minor, it is difficult to quantify the impact of this risk. | Client needs change. Shifting markets. Emergence of new technology. | 3 | 2 | Upon receipt of a new requirement, try to incorporate it into the existing plan. | 2023-01-16 | 18/01/2023: Upon receiving an updated requirement to our weekly plan, we were able to test our agility and make the changes effectively. | We were able to handle changing requirements well.
Client Threats
Client Incurs Unexpected Costs | The client will be unhappy if they incur costs which have not been clearly laid out for them to sign off on. The client may lose faith in us to provide them with a reliable solution if their actual costs do not match our projections. | Mis-calculation of costs. Incomplete cost analysis. Under representing the amount of resources that the client will require. | 2 | 3 | Create a complete and carefully calculated cost report and analysis. | 2023-01-16 | 19/01/2023: Cost analysis report created using data sourced from AWS and with tailored costs for the client's needs. | We were able to create a cost anaysis report which takes into account the specific resources present within our solution.
Client Not Satisfied with Solution | If our solution is lacking in the eyes of the client, we will damage their image of us. Every client is important and so it is vital that we meet their high expectations. | One or more aspects of our solution aren't functional. Interact with the client poorly. Not clearly explaining our solution and rationale. | 3 | 5 | Build our solution to the highest standard, taking into account best practices throughout. | 2023-01-16 | 19/01/2023: Ensure that our planned presentation is appropriate for the intended audience and that our documentation is up to date and completed to a higher standard. | Despite not having a fully working pipeline, the team anticipates that the presentation will be well received, based on our previous successes.